## Sheet1
System Name | Videogame Trading System
Members: | Rei Samson Agravante
Mikhail James Navarro
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2
1. USER AUTHENTICATION
1.1. Integrate with Database | Mikhail James Navarro |  |  | To do
1.2. User Login/Signout Functionality | Mikhail James Navarro |  |  | To do
1.3. User Registration Functionality | Mikhail James Navarro |  |  | To do
2. INITIAL DESIGN (Figma) | Rei Samson Agravante
3. API INTEGRATION
3.1. API Fetch Functionalities | Rei Samson Agravante |  |  | Done
4. ENTITIES
4.1. User
4.1.1. Create User Model | Mikhail James Navarro |  |  | Done
4.1.2. Create User Views/Template/URLs | Mikhail James Navarro |  |  | Done
4.2. Watchlist
4.2.1. Create Watchlist Model | Rei Samson Agravante |  |  | Done
4.2.2. Create Watchlist Views/Template/URLs | Rei Samson Agravante |  |  | Done
4.3. Forums
4.3.1. Create Forums Model | Rei Samson Agravante |  |  | Done
4.3.2. Create Forums Views/Template/URLs | Rei Samson Agravante |  |  | In Progress
4.4. Price History
4.4.1. Create Price History Model | Rei Samson Agravante |  |  | Done
4.4.2. Create Price History Views/Template/URLs | Rei Samson Agravante |  |  | On-hold
5. WEBPAGE
5.1 FAQs Page |  |  |  | Done
6. FINALIZE DESIGN |  |  |  | In Progress